## Sheet1
RESCUBOT
|  |  | Miguel |  | Marwa |  | Vincent |  | Nur |  | Abeeb |  | Charles
# | Task | Summary | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done
1 | Complete the diagrams | After agree with the requirements each two members will work on a diagram. Deadline: Monday at 16:00 | Activity | 2021-04-11 | Requirement | 2021-04-10 | Requirement | 2021-04-10 | Use case | 2021-04-11 | Use case | 2021-04-11 | Activity Diagram | 2021-04-11
2 | Complete the diagrams | Update the 3 previous diagrams and share 3 others | Bdd | 2021-04-21 | bdd | 2021-04-21 | Statemachine Diagram | 2021-04-21 | Constrains diagram | 2021-04-21 | Constrains diagram | 2021-04-21 | Sequence diagram | 2021-04-21
3 | Diagrams and model | Update the diagrams and do the new assigned ones. Deadline on Thursday 29 at 09:00 | Detection and communication sub-systems | 2021-04-29 | Robot system | 2021-04-29 | Navigation Sub-sytem | 2021-04-29 | Raw sketch prototype | 2021-04-28 | Power sub-system | 2021-04-29 | Driving sub-system | 2021-04-28
4 | Diagrams review | Upgrade the diagrams regarding feedback from professor | Review diagrmas | 03-05-2021 | Review diagrmas | 2021-05-03 | Review diagrmas |  | Review diagrmas |  | Review diagrmas |  | Review diagrmas
5 | Prototyping task 1 | shared tasks based on required Presention (research on different techniques to walk on land and drive on water ) | Research |  | Research | 2020-05-06 | Research | 2020-05-06 | Research | 2020-05-06 | Research | 2020-05-06 | Research | 2020-05-06
6 | Prototyping task 2 | shared tasks based on required Presention | Legs hand sketch | 2020-05-13 | Materials needed +Chassis hand sktch | 2020-05-13 | arms handsketch | 2020-05-13 | Big turbine hand sketch | 2020-05-13 | small trbuine |  | Dom sketch | 2020-05-13
7 | Prototyping task 3 | shared tasks based on required Presention | Solidwork (3Dmodel ,Legs ,Case and assemble) | 2020-05-20 | Update chassis hand sketch | 2020-05-20 | Calculate power consumption | 2020-05-20 | Solidwork (turbine) | 2020-05-20 | Calculate components weight | 2020-05-20 | 2D animation ,solid work (chassis ) | 2020-05-20
8 | Prototyping task 4 | Finilize the prototupe and prepare presentation | Solidworks legs reinforcement, sensors bases, joint tolerances |  | Electronic components |  | Electronic Componenets |  | Solidworks |  | Electonic components |  | Animation