## Sheet1
RESCUBOT
|  |  | Miguel |  | Marwa |  | Vincent |  | Nur |  | Abeeb |  | Charles
# | Task | Summary | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done | ToDo | Done
1 | Complete the diagrams | After agree with the requirements each two members will work on a diagram. Deadline: Monday at 16:00 | Activity | 2021-04-11 | Requirement | 2021-04-10 | Requirement | 2021-04-10 | Use case | 2021-04-11 | Use case | 2021-04-11 | Activity Diagram | 2021-04-11
2 | Complete the diagrams | Update the 3 previous diagrams and share 3 others | Bdd | 2021-04-21 | bdd | 2021-04-21 | Statemachine Diagram | 2021-04-21 | Constrains diagram | 2021-04-21 | Constrains diagram | 2021-04-21 | Sequence diagram | 2021-04-21
3 | Diagrams and model | Update the diagrams and do the new assigned ones. Deadline on Thursday 29 at 09:00 | Detection and communication sub-systems | 2021-04-29 | Robot system | 2021-04-29 | Navigation Sub-sytem | 2021-04-29 | Raw sketch prototype | 2021-04-28 | Power sub-system | 2021-04-29 | Driving sub-system | 2021-04-28
4 | Diagrams review | Upgrade the diagrams regarding feedback from professor | Review diagrmas |  | Review diagrmas |  | Review diagrmas |  | Review diagrmas |  | Review diagrmas |  | Review diagrmas